## Wine3 Gradesheet
Date | Task | Description | Deliverable | Weight(%) | Grade
1/20/2005(complete) | Schedule | Come up with a preliminary schedule for the project | The schedule in Wiki | 1
1/21/2005(complete) | Project 0 | Install Windows and Linux | Report on Wiki | 2
1/21/2005(complete) | Project 1 | Build Wine | Report on Wiki | 2
1/28/2005(complete) | Project 2 | Run base conformance test | Test results on Wiki | 2
1/28/2005(complete) | Select DLL | Research candiate DLL's and choose the one we will work on | Report on Wiki | 1
2/4/2005(complete) | Design | Plan the conformance test, determine most commonly used functions and arguments. | Report on Wiki | 4
2/4/2005(complete) | Alpha | Create first Win32 app, add base function tests. Run in Windows | Source | 6
2005-02-14 | Beta | Have the most common calls implemented. Submit to wine-test-devel for review. | Source | 4
2005-02-18 | MT Present | Present Basics of Wine, as well as an introduction to writing compliance tests | Presentation | 3
2005-02-21 | Submit | Modify based on feedback, and submit to Wine list. Modify based on feedback from the winehq list and resubmit every few days. | Source | 5
| Acceptance | Test accepted into winehq source tree | Email Notification | 5
| Onwards | Continue upgrading test suite, preparing to submit as additional patch once test is accepted | Source
Finals Week | Final Present | Show final tests, execution on Win & Linux, as well as eviolution of code over CVS commits | Presentation | 5
40